## Total Project Tracking
Total Project Tracking
Information in columns A–E describes each function; columns F–I record implementation progress. Source: commits by vinhntkse180756 on origin/vinh and origin/vinh2, checked 12 Oct 2026.
# | Screen/Function | Feature | Actor | Screen/Function Description | Complexity | In Charge | Status | Update Details
1 | Registration, Login and Access Control | Authentication | Guest, User, Admin | Implements account registration, login, JWT authorization, session verification and logout. The backend checks roles, lock state and revoked tokens for protected requests. | Complex | Từ Vinh | Done | 1837ada, 6fa39a8, 36375e4: Auth API, roles, JWT and session tests.
2 | Forgot and Reset Password | Authentication | Guest | Sends a password reset link through configured email and validates a short-lived, one-use token. Changes the password and invalidates older sessions while limiting repeated requests. | Medium | Từ Vinh | Done | 36375e4: reset flow, SMTP, token storage and tests.
3 | Personal Information and Diet | Profile | User, Admin | Shows and updates the current user profile, contact information and vegetarian diet. Connects the profile form to the backend API. | Simple | Từ Vinh | Updated | 20de3d4, a9c92be: profile CRUD, diet selection and FE mapping.
4 | Body Metrics, Allergies and Avoided Foods | Profile | User, Admin | Manages body measurements, allergies and avoided foods. Calculates BMI/TDEE on the backend and shows estimate results in the profile screen. | Medium | Từ Vinh | Updated | 20de3d4, a9c92be: nutrition rules, list CRUD and UI integration.
5 | Admin Member Management | Administration | Admin | Lists and searches members, shows details and status history, and locks or unlocks accounts with reasons. Connects the member page to the real Admin API. | Complex | Từ Vinh | Updated | 20de3d4, 73f30c3, e743ec9, 1b2710c: API, UI and tests.
6 | Admin Dashboard | Administration | Admin | Returns real member, core-data, content and review-queue counts with recent activity. Routes the dashboard UI to live backend summaries. | Medium | Từ Vinh | Updated | ffc06c2, 8e6a30a, c0289b5: dashboard UI and data API.
7 | Articles, Drafts and Review Versions | Articles | Guest, User, Admin | Provides published article listing, author-owned drafts and submission to AI/Admin review. Tracks versions and feedback while retaining the approved public article during later revisions. | Complex | Từ Vinh | Done | 8e6a30a: article API, draft workflow and moderation integration.
8 | Comments, Moderation and Reactions | Comments | Guest, User, Admin | Provides comment lists, replies, author edits and Admin hide/remove actions. Records article helpful votes and video/comment likes with real counts. | Complex | Từ Vinh | Done | c0289b5: comment/reaction APIs, domain rules and tests.